## Sheet1
Task | Completion Date | Days
BackEnd
Prepare class diagram, object diagram and database diagram | 2022-05-31 | 1
Implement folder stucture and datamodels | 2022-06-01 | 1
implement APIs | 2022-06-06 | 3
FrontEnd
Prepare wireframs for pages | 2022-06-07 | 1
Implement generic component and customer component | 2022-06-09 | 2
Implement page component with API calling | 2022-06-13 | 2